## Sheet1
Description | Evaluation | Probability | Impact Level | Responsibility | Response | Control Measures | Probability post implementation | Impact Level post implementation | Control Measures post implementation
The website unable to be accessed | Website down | low | high | David | user sends a message to inform of the problem and David responds to the problem and puts website back up | docker swarm is used and multiple replicas made of each container so connection can be reestablished | low | high
The website being slow as multiple people try to use it | Slow or down website | medium | medium | David | add more space (increase sever space/ number of replicas/ limit the numbers on the page) | docker swarm is used and multiple replicas made of each container so number of containers can increased | low | medium | increase the number of workers and mangers in the swarm
Someone using Jenkins to change or steal data | Data stolen or changed | medium | high | David | assess the damage and change passwords and usernames | limit Jenkins to only the processes it needs and not full access
VM for database goes down | loss of service and data | low | high | David | user sends a message to inform of the problem and restart/ start a new sever copying any lost data | Take regular backups of the database
VM for Jenkins goes down | loss of service and data | low | low | David | user sends a message to inform of the problem and restart/ start a new sever copying any lost data | script saved in the code pushed to the repository, the website is run on manger vm so no loss in service | low | medium | set up a backup Jenkins server with run code added
Container goes down | loss of service and data | low | medium | David | message sent to David and containers checked and restarted if needed | docker swarm used so broken containers replaced | low | low | create multiple replicas in the docker-compose yaml for redundancy
manager node goes down | loss of service and data | low | high | David | message sent to David and nodes check and manager restarted | multiple manger nodes created so if one fails another can take its place
worker node goes down | loss of service and data | low | medium | David | message sent to David and nodes check and worker restarted | docker swarm used so containers moved to a working manager/worker node | low | low | make more worker nodes to increase redundancy